Project Monitoring Report

of

Children Education Programme             (CEP Project)

Period: January - June, 2011

Submitted to: TdH-Netherlands

Submitted By:

People’s Oriented Program Implementation (POPI)

5/11-A, Block-E, Lalmatia, Dhaka-1207

E-mail: popi@bdmail.net;

Website: www.popibd.org

Table of Contents

Page No.

Chapter-1                                                                                          			3

- Background information                                                                  			3

- Results 			3

- Summary of the activity monitoring report			5

Chapter-2			6

Detail accounts of activities			6

- Early Child Development (ECD) 			6

- Formal Primary Schools                                                                   			9

- Community and Registered Primary School			13

- Orphanage			17

- Project monitoring			17

Chapter-3			18

1. Conclusion			18

Chapter-1

1. Background information:

Education must be viewed as fundamental human rights and catalyst for human development. Poor and marginalized people have the rights to education. Assurance of entitlement to education is not an act of charity. Education must reflect people’s demand, problems and equip them with appropriate solution towards improved life and livelihood. From the experiences and analyzing the contextual change, POPI realizes that the traditional forms education is not enough to address the issues of people’s empowerment and claiming their rights.

CEP Project has been performing a series of activities to enhance the education level of the vulnerable children of project area and has always given top priority in establishing the rights of the children. The specific objective is to promote the children rights in project area and purpose of the program is establishment of universal primary education for the deprived children of the project areas.

The program has gone through 6th phase of implementation with four major components. These are early childhood development, primary education through Formal primary school, to support registered & community primary school and to support orphanage including Education, Shelter uniform & food.

The report is the Project Monitoring Report of CEP Project for the period of January 2011 to June, 2011 which reflects activities performance against expected results and achievement of purpose of the program.

The Activity monitoring has been conducted through participatory process by involving beneficiaries, stakeholders and personnel’s of the project. 4 specific results are expected to be achieved at the end of project period. The expected results of the project are as follows;

2. Results:

| Results qualitative | Results quantitative(indicators) |
| --- | --- |
| 1. Children have access Early Childhood Development (ECD) program. | 1.1.1 ) No. of ECD centers established Year-1 Year 2 Year 3 20 20 20 1.1.2) No. of children enrolled Year-1 Year 2 Year 3 600 600 600 1.1.3) Drop out rate reduced Year-1 Year 2 Year 3 03% 02% 01% 1.1.4) Percentage of average attendance of children increased Year-1 Year 2 Year 3 97% 97% 98% 1.1.5) No. of trained teachers on ECD Year-1 Year 2 Year 3 20 20 20 1.1.6) No. of participants aware of child rights through parents teachers meeting Year-1 Year 2 Year 3 600 600 600 |
| 2. Children have access to primary education organized by POPI. | 1.2.1) No. of Primary School establishment Year-1 Year 2 Year 3 06 06 06 1.2.2) No. of children enrolled Year-1 Year 2 Year 3 900 900 900 1.2.3) Rate of dropout reduced Year-1 Year 2 Year 3 04% 3.5% 3% 1.2.4) Percentage of average children attendance increased Year-1 Year 2 Year 3 96% 97% 97% 1.2.5) No. of trained teacher on primary education Year-1 Year 2 Year 3 24 24 24 1.2.6) No. of children promoted to next classes Year-1 Year 2 Year 3 900 900 900 1.2.7) No. of children completed primary school (grade-V) Year-1 Year 2 Year 3 180 180 180 1.2.8) No. of participants aware of child rights Year-1 Year 2 Year 3 900 900 900 1.2.9) No. of SMC members trained of child rights Year-1 Year 2 Year 3 18 18 18 1.2.8) No. of schools received donation of land from community Year-1 Year 2 Year 3 06 06 06 |
| 3. Children have access to community and registered primary schools | 1.3.1) No. of Community and registered Primary School supported Year-1 Year 2 Year 3 10 10 10 1.3.2) No. of children enrolled Year-1 Year 2 Year 3 2900 2900 2900 1.3.3) Rate of dropout reduced Year-1 Year 2 Year 3 15% 13% 10% 1.3.4) Percentage of average children attendance increased Year-1 Year 2 Year 3 85% 86% 87% 1.3.5) No. of children promoted to next class Year-1 Year 2 Year 3 2900 2900 2900 1.3.6 No. of children promoted primary school (grade V) Year-1 Year 2 Year 3 340 345 350 1.3.7) No. of trained teacher on primary education Year-1 Year 2 Year 3 50 50 50 1.3.8) No. of participants aware of child rights through quarterly parents teacher meeting Year-1 Year 2 Year 3 2900 2900 2900 1.3.9) No. of SMC members trained on child rights Year-1 Year 2 Year 3 30 30 30 |
| 4. Orphan children have access to education | 1.4.1) No. of children enrolled in orphanage Year-1 Year 2 Year 3 55 55 55 1.4.2) No. of children enrolled in primary school Year-1 Year 2 Year 3 22 22 22 1.4.3) No. of children enrolled in secondary school Year-1 Year 2 Year 3 33 33 33 1.4.4) No. of school children promoted to next classes Year-1 Year 2 Year 3 55 55 55 1.4.5) No. of children completed primary school (grade-5) Year-1 Year 2 Year 3 1 5 8 1.4.6) No. of children completed secondary school Year-1 Year 2 Year 3 3 5 8 1.4.7) No. of children received shelter, food and non-food items Year-1 Year 2 Year 3 55 55 55 |

3. Summary of the Activity monitoring Report:

The summary of the Activity monitoring report has been prepared from the weekly and monthly monitoring of teachers and project staff including project coordinator during the reporting period.

- A total of 620 children were enrolled in 20 ECD centers against the target of 620 where 620 children assessed for their physical and mental development.

No child dropped out during this time.

- % of average attendance of children in ECD was 97% against the target of 97%. 20 ECD teachers participated in monthly refreshers to improve their teaching-learning abilities.

- In January 2011, a total of 938 children (484 boys and 454 girls) were enrolled in 06 formal primary schools against the target of 900. During the reporting period, 30 children (23 boys and 07 girls) were newly admitted and 14 children (08 boys and 06 girls) were dropped out from 06 schools. At the end of June, 954 children (499 boys and 455 girls) are now continuing.

- Out of them 122 children of class-V will be participated in the Primary Terminal Examination that will held in November 2011.

- 24 teachers formal primary school participated in monthly refreshers and 95% teachers attend in refreshers training and got trained on education.

- Total 34 parents meeting were conducted during reporting period against 12. 94% parents participated in monthly parents meetings and aware about in child rights.

- During the reporting period 24 SMC meeting were organized against the target of 12 where important decision had taken on behalf of children education. 77% SMC members were participated in the meetings.

- 30 SMC members of 04 Community and Registered Primary Schools were trained about the child rights issue to build up their capacity for better performance in school management.

- In January 2011, a total of 3508 children (1717 boys and 1791 girls) were enrolled in 10 Community and Registered Primary Schools against the target of 2900.

During the reporting period, 180 children (142 boys and 38 girls) were newly admitted and 06 children

(03 boys and 03 girls) were dropped out.  At the end of June, 3682 children (1856 boys and 1826 girls)

are   now continuing.

- Out of them 429 children of class-V will be participated in the Primary Terminal Examination that will held in November 2011.

- 80% guardians were aware about the Child Rights through Parents- Teacher meetings.

- 02 orphan students participated in the Secondary Examination and passed successfully.

Chapter-2:

RESULT-1

1. Access to Early Childhood Development Established:

Performances of ECD:

The United Nation Convention on the Rights of the Child is a live document, agreed by the almost all of the member countries to follow the convention’s right and regulation.

The convention strongly emphasized to cover under 54 articles to define child (0-18 years) developed a cluster of child right i.e. survival, protection, development and participation. The convention strongly defined the 4 principles i.e. discrimination, the superior interest and welfare of child, role of parents and respect to child opinion in order to established child rights and child development. Correspondence with the above rights and principles, along with EFA declaration, the EFA goal 1 is the “expansion of early childhood care and education programs”, and was re-affirmed in Dakar as “expanding and improving comprehensive early childhood care and education, especially for the most vulnerable and disadvantaged children.”

ECD is a vital element to make up the convention commitment. Under this, pre-primary education (ECD) is considered to be the focal sub sector where to incorporate the 4 major issues of development, survival, protection and effective participation of children for building human capital and national assets.

CEP has taken ECD intervention to prepare the children for formal education with right attitude by physical and mental development. To ensure the quality of Early Childhood Development Programme, it has given emphasis on introducing the appropriate course curricula, capacity building of teachers & staffs for providing good lesson and activities to achieving the desire level of children development.

1.1.) Nr of children enrolled: In January 2011, 620 children (292 boys and 328 girls) were enrolled in 20 ECD centers against the target of 600. During the reporting period, no child dropped out from the program.

Table-1: Enrolment of the children in different primary schools ECD

| SL No | Name of the School | Enrolled students | Remarks |
| --- | --- | --- | --- |
|  |  | Boys | Girls | Total |  |
| 1 | Pultakandi | 13 | 17 | 30 |  |
| 2 | Mirerchar | 11 | 24 | 35 |  |
| 3 | F.M.Alam | 09 | 21 | 30 |  |
| 4 | Soisuti | 15 | 15 | 30 |  |
| 5 | South Salua | 14 | 21 | 35 |  |
| 6 | Md. Ali FPS-1 | 16 | 14 | 30 |  |
| 7 | Md. Ali FPS-2 | 15 | 15 | 30 |  |
| 8 | Hazi Kalu RPS | 14 | 16 | 30 |  |
| 9 | Akbor Nagar RPS | 15 | 15 | 30 |  |
| 10 | Noagoan RPS | 15 | 20 | 35 |  |
| 11 | Parikharpar RPS | 16 | 19 | 35 |  |
| 12 | Fariroghunathpur CPS-1 | 16 | 14 | 30 |  |
| 13 | Fariroghunathpur CPS-2 | 15 | 15 | 30 |  |
| 14 | Imamerchar CPS-1 | 19 | 11 | 30 |  |
| 15 | Imamerchar CPS-2 | 15 | 15 | 30 |  |
| 16 | Guchamara CPS-1 | 15 | 15 | 30 |  |
| 17 | Guchamara CPS-2 | 11 | 19 | 30 |  |
| 18 | Kamarkanda CPS | 16 | 14 | 30 |  |
| 19 | Rajakatha CPS | 14 | 16 | 30 |  |
| 20 | Atkapara CPS | 18 | 12 | 30 |  |
| Total |  | 292 | 328 | 620 |  |

1.2) % of average attendance: During the reporting period, attendance of the children were recorded daily and reported monthly. Average attendance of the children was 97% against the target 97%. Attendance of children at each ECD centre is presented in the table-2.

Table-2: Average monthly attendance of ECD centers.

| Sl No | Name of school | Monthly attendance | Average | All average % |
| --- | --- | --- | --- | --- |
|  |  | Jan | Feb | March | April | May | June |  |  |
| 1 | Mirerchar (FPS) | 98 | 98 | 99 | 98 | 98 | 96 | 98 | 97 |
| 2 | Pultakandi (FPS) | 97 | 97 | 98 | 94 | 93 | 93 | 95 |  |
| 3 | Mohammad Ali (FPS)-1 | 98 | 98 | 98 | 98 | 98 | 97 | 98 |  |
| 4 | Mohammad Ali (FPS)-2 | 99 | 98 | 98 | 99 | 99 | 98 | 98 |  |
| 5 | M.F. Alam (FPS) | 97 | 98 | 97 | 98 | 98 | 99 | 98 |  |
| 6 | Choto Soisuti (FPS) | 93 | 93 | 92 | 92 | 93 | 97 | 93 |  |
| 7 | South Salua (FPS) | 99 | 98 | 98 | 96 | 97 | 99 | 98 |  |
| 8 | Haji Kalu Miah RPS | 99 | 98 | 99 | 99 | 99 | 97 | 98 |  |
| 9 | Akbar Nagar RPS | 98 | 97 | 97 | 97 | 98 | 97 | 97 |  |
| 10 | Porikharpar RPS | 93 | 97 | 93 | 95 | 95 | 98 | 95 |  |
| 11 | Naogaon RPS | 96 | 95 | 89 | 95 | 87 | 93 | 92 |  |
| 12 | Imamer Char (CPS)-1 | 98 | 98 | 97 | 97 | 97 | 97 | 97 |  |
| 13 | Imamer Char (CPS)-2 | 97 | 97 | 97 | 97 | 97 | 97 | 97 |  |
| 14 | Gochamara (CPS)-1 | 99 | 99 | 98 | 98 | 98 | 98 | 98 |  |
| 15 | Gochamara (CPS)-2 | 99 | 98 | 98 | 97 | 97 | 97 | 98 |  |
| 16 | Fari Ragunathpur (CPS)-1 | 98 | 99 | 98 | 98 | 98 | 97 | 98 |  |
| 17 | Fari Ragunathpur (CPS)-2 | 98 | 98 | 98 | 96 | 97 | 97 | 97 |  |
| 18 | Kamarkanda (CPS) | 98 | 98 | 99 | 98 | 97 | 99 | 98 |  |
| 19 | Chotorajakata (CPS) | 97 | 97 | 97 | 98 | 97 | 98 | 97 |  |
| 20 | Atkapara (CPS) | 93 | 98 | 99 | 98 | 99 | 97 | 97 |  |
| Total |  | 97 | 97 | 96 | 97 | 97 | 97 | 97 |  |

1.3) Children development assessed:

In June 2011, a total of 613 children (289 boys and 324 girls) were participated in the half yearly assessment against the target 620. Student’s performance has been evaluated to justify their physical and mental development. Individual school performance and area of weakness of competencies have find out by this assessment.

Table-3: Assessment result of ECD.

| Sl. No | Name of the centre | Total learners | Attend in exam | Assessment result |
| --- | --- | --- | --- | --- |
|  |  | B | G | T | B | G | T | A (+80) | B (60-79) | C (40-59) | D (-40) | Total |
| 1 | Mirerchar | 11 | 24 | 35 | 11 | 22 | 33 | 16 | 10 | 07 | - | 33 |
| 2 | Pultakandi | 13 | 17 | 30 | 10 | 17 | 27 | 14 | 08 | 05 | - | 27 |
| 3 | Mohammad Ali-1 | 16 | 14 | 30 | 16 | 14 | 30 | 19 | 08 | 07 | - | 30 |
| 4 | Mohammad Ali-2 | 15 | 15 | 30 | 15 | 15 | 30 | 16 | 10 | 04 | - | 30 |
| 5 | M.F.Alam | 09 | 21 | 30 | 09 | 21 | 30 | 21 | 05 | 04 | - | 30 |
| 6 | Soisuti | 15 | 15 | 30 | 15 | 15 | 30 | 18 | 08 | 04 | - | 30 |
| 7 | S.Salua | 14 | 21 | 35 | 14 | 21 | 35 | 16 | 13 | 06 | - | 35 |
| 8 | Haji kalu RPS | 14 | 16 | 30 | 14 | 16 | 30 | 15 | 10 | 05 | - | 30 |
| 9 | Parikherper RPS | 16 | 19 | 35 | 16 | 19 | 35 | 30 | 04 | 01 | - | 35 |
| 10 | Akbarnagar RPS | 15 | 15 | 30 | 15 | 15 | 30 | 14 | 10 | 06 | - | 30 |
| 11 | Noagoan RPS | 15 | 20 | 35 | 15 | 18 | 33 | 12 | 15 | 06 | - | 33 |
| 12 | Imemerchar -1 | 15 | 15 | 30 | 15 | 15 | 30 | 14 | 09 | 07 | - | 30 |
| 13 | Imemerchar -2 | 16 | 14 | 30 | 16 | 14 | 30 | 16 | 10 | 04 | - | 30 |
| 14 | Gusamara CPS- 1 | 15 | 15 | 30 | 15 | 15 | 30 | 09 | 13 | 08 | - | 30 |
| 15 | Gusamara CPS- 2 | 11 | 19 | 30 | 11 | 19 | 30 | 11 | 10 | 09 | - | 30 |
| 16 | Ragunathpur -1 | 19 | 11 | 30 | 19 | 11 | 30 | 08 | 15 | 07 | - | 30 |
| 17 | Ragunathpur -2 | 15 | 15 | 30 | 15 | 15 | 30 | 04 | 15 | 11 | - | 30 |
| 18 | K.Kanda CPS | 16 | 14 | 30 | 16 | 14 | 30 | 14 | 12 | 04 | - | 30 |
| 19 | R. Kata CPS. | 14 | 16 | 30 | 14 | 16 | 30 | 12 | 11 | 07 | - | 30 |
| 20 | AtkaparaCPS | 18 | 12 | 30 | 18 | 12 | 30 | 17 | 10 | 03 | - | 30 |
|  | Total | 292 | 328 | 620 | 289 | 324 | 613 | 295 | 206 | 112 |  | 613 |

From the above data, it is revealed us that 99% children have been assessed where 501(82%) children developed well physically and mentally. 112 (18%) children did not develop according to desire level. Seven children did not take part in the assessment from the schools of Mirerchar, Pultakandi and Noagoan. All the children were absent in the assessment due to illness.

1.4) Nr. of Parents meetings organized in ECD:

Bimonthly parents meetings were held in 20 ECD centers. Participation of guardians was found very well. Although bimonthly parents meeting suppose to conduct but monthly meeting was conducted for the better concern of the children. During the period of January- June 2011, a total of 117 parents meetings were held against the target of 60. Different issue related to children rights was discussed in the meetings.

Table:-4:    Attendance of guardians in parents meetings in ECD.

| Parents meetings |
| --- |
| Month | Target | Achievement |
|  | Nr. of meeting | Participants | Nr. of meeting | Participants |
| January | - | - | 18 | 498 |
| February | 20 | 620 | 19 | 549 |
| March | - | - | 20 | 545 |
| April | 20 | 620 | 20 | 561 |
| May | - | - | 20 | 546 |
| June | 20 | 620 | 20 | 523 |

1.5) Refreshers training for ECD teachers:

During the reporting period of January- June’2011, a total of 07 refreshers training were conducted against the target of 06. On an average, 97% teachers were participated in the training to develop themselves to providing good lesson.

In the refreshers training, different technique and methodologies were discussed to increase the competencies of teachers as planned. Lessons provided by teachers were supervised regularly for judging the quality of teaching. Necessary support was given to improve the performance of teachers.

Month wise teacher’s attendance in monthly refreshers training is presented in the table below:-

Table -5: Attendance of ECD teachers in monthly refreshers training.

| Name of month | Target | Achieved | Deviation | Remarks |
| --- | --- | --- | --- | --- |
|  | Refreshers | Pts | Refresher | Pts |  |  |
| Jan | 01 | 20 | 02 | 39 | 01 | Md. Ali Parikharpar |
| Feb | 01 | 20 | 01 | 19 | 01 |  |
| March | 01 | 20 | 01 | 19 | 01 |  |
| April | 01 | 20 | 01 | 20 | - |  |
| May | 01 | 20 | - | - |  |  |
| June | 01 | 20 | 02 | 39 | 01 |  |

Four teachers did not participate in refreshers training due to their physical sickness.

RESULT-2

2. Access to Primary Education organized by POPI:

Performance of FPS:

Bangladesh is committed to promote quality primary education. With this aim in view, it has undertaken missions for meeting the EFA goals combined with MDG and PRSP goals. Considering peoples’ empowerment with knowledge and skills as the most vital component of human development for poverty reduction, the government formulated education policy to contribute to fulfilling EFA goals and alleviating poverty.

Primary education is the fundamental rights of children. Government of Bangladesh is committed to ensure the rights of basic education. To fulfill this commitment, from 1992 the primary education was made compulsory in Bangladesh to address the fundamental rights of children. Government has given support by supplying free textbook and free of cost admission in school. As a result, access to primary education has increased considerably. In spite of these effort by government, a portion of children remained out of school. POPI's Formal Primary Schools intervention has been giving support for those out of school and deprived children.  Each of formal primary schools has students of class I to class V.

2.1) Nr of children enrolled: In January 2011, a total of 938 children (484 boys and 454 girls) were enrolled in 06 formal primary schools against the target of 900.

During the reporting period, 30 children (23 boys and 07 girls) were newly admitted and 14 children (08 boys and 06 girls) were dropped out from 06 schools. At the end of June, 954 children (499 boys and 455 girls) are now continuing.

Table-6: Enrolment of the children in different FPS

| Name of school | Category | Class - I | Class – II | Class - III | Class - IV | Class - V | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pultakandi FPS | Boys | 20 | 18 | 16 | 20 | 13 | 87 |
|  | Girls | 12 | 15 | 14 | 08 | 09 | 58 |
|  | Total | 32 | 33 | 30 | 28 | 22 | 145 |
| Mirerchar FPS | Boys | 21 | 23 | 32 | 16 | 13 | 105 |
|  | Girls | 14 | 13 | 38 | 17 | 16 | 98 |
|  | Total | 35 | 36 | 70 | 33 | 29 | 203 |
| M.F.Alam FPS | Boys | 17 | 19 | 25 | 10 | 05 | 76 |
|  | Girls | 22 | 15 | 12 | 12 | 13 | 74 |
|  | Total | 39 | 34 | 37 | 22 | 18 | 150 |
| Soisuti FPS | Boys | 26 | 18 | 13 | 12 | 08 | 77 |
|  | Girls | 14 | 14 | 17 | 18 | 14 | 77 |
|  | Total | 40 | 32 | 30 | 30 | 22 | 154 |
| South Salua FPS | Boys | 24 | 12 | 18 | 09 | 15 | 78 |
|  | Girls | 10 | 19 | 16 | 22 | 08 | 75 |
|  | Total | 34 | 31 | 34 | 31 | 23 | 153 |
| Md. Ali FPS | Boys | 39 | 17 | 09 | 06 | 05 | 76 |
|  | Girls | 34 | 19 | 06 | 11 | 03 | 73 |
|  | Total | 73 | 36 | 15 | 17 | 08 | 149 |
| Grand Total | Boys | 147 | 107 | 113 | 73 | 59 | 499 |
|  | Girls | 106 | 95 | 103 | 88 | 63 | 455 |
|  | Total | 253 | 202 | 216 | 161 | 122 | 954 |

2.2) % of average attendance:

As per Millennium Development Goal (MDG), 100% children would complete their primary education by 2015. Enrollment Rate in primary education has increased significantly over the last two decades due to various efforts by the government and non government organization. However, the completion rate in primary education is almost half of the enrolled students. This indicates that a large number of students are dropping out from the primary education system.

To increase the attendance of children in school, some routine work, such as parents meeting, SMC meeting and house hold visit of absentee student, is to do regularly in formal primary schools.  Month wise student attendance is presented in the table below:-

Table-7: Average attendance of Formal Primary School.

| Sl No | Name of school | Monthly attendance | Average | T.A. Attendance |
| --- | --- | --- | --- | --- |
|  |  | Jan | Feb | March | April | May | June |  |  |
| 1 | Mirerchar | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 97 |
| 2 | Pultakandi | 97 | 98 | 97 | 98 | 94 | 97 | 97 |  |
| 3 | Mohammad Ali | 95 | 92 | 99 | 99.6 | 99.7 | 97 | 97 |  |
| 4 | Faisal Alam | 98 | 98 | 98 | 98 | 98 | 98 | 98 |  |
| 5 | Choto Soisuti | 98 | 98 | 95 | 97 | 97 | 98 | 97 |  |
| 6 | South Salua | 97 | 97 | 98 | 96 | 97 | 98 | 97 |  |

During the reporting period, average attendance was 97% against the target of 97%.

2.3) Nr of children attends in 1st terminal examination (I-IV):

1st terminal examination (Class I-IV) was held in six formal primary schools along with government primary schools according to the direction of education department of Bangladesh. Upazila Education Office was conducted this examination by supplying questionnaire and schedule of examination.

Table-8: First Terminal Examination result of Formal Primary Schools:

| Name of School | Total Student | Total no. of Student participated in the exam | Deviation | Grade – A (80+) No. of Student | Grade – B (60-79) No. of Student | Grade – C (40-59) No. of Student | Grade – D (-40) No. of Student |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mirarchar | 203 | 203 | - | 143 | 49 | - | 11 |
| Mohammad Ali | 149 | 149 | -- | 40 | 26 | 55 | 28 |
| Pultakandi | 145 | 145 | - | 15 | 38 | 80 | 12 |
| Faisal Alam | 150 | 150 | - | 80 | 60 | - | 10 |
| South Salua | 153 | 153 | - | 31 | 20 | 77 | 25 |
| Soisuti | 154 | 142 | 12 | 26 | 67 | 36 | 13 |
| Total | 954 | 942 | 12 | 335 | 260 | 248 | 99 |

From the above data, it is reveal us that all the students of 05 FPS schools out of 06, were participated in the examination. 12 students from Soisuti Formal Primary School were not attended in the examination due to incident of agitation among the villagers.

In the examination, a total of 942 children were participated in six formal primary schools out of 954 children. Examination was held in May 2011. Out of them 335 (36%) children scored grade-A (80+), 260 (28%) children scored grade-B (60-79), 248 (26%) children scored grade-C (40-59) and 99 (10%) children scored grade-D (40-).

From the above data it is also shown that students from Mirerchar and Faisal Alam performed in satisfactory level where 70% students from Mirerchar and 53% students from Faisal Alam scored grade-A. In Pultakandi, performance was so poor that 55% children scored grade-C. For these low performance schools, by identifying weak students and support them, frequent visit for those schools by supervisor, necessary action has been taken to increase the performance within the next terminal examination.

2.4) Nr. of children enrolled for Primary Terminal Examination (Grade V):

Primary Terminal Examination-2011 will be held in 19th November to 26th November, 2011 throughout the country. The education board all ready circular the above mentioned date by public notice. Information about the students who will be appeared for Primary Terminal Examination-2011 has been sent to Upazila Education Office by the respective schools according to the prescribe format.

In this year, students from all 06 formal primary schools will be participated in this examination while last year 05 schools out of 06 appeared in the primary terminal examination. A total of 122 students (59 boys and 63 girls) will be participated while last year 132 students were sat for examination.

From January 2011, teachers have been arranging special coaching class for the grade-V children for better performance.

Table -9: Enrolled students for Primary Terminal Examination for FPS

| Name of the schools | # of student | Nr of students enrolled for exam | Deviation | Remarks |
| --- | --- | --- | --- | --- |
|  | B | G | T | B | G | T |  |  |
| Mirerchar | 13 | 16 | 29 | 13 | 16 | 29 | - |  |
| Md. Ali | 05 | 03 | 08 | 05 | 03 | 08 | - |  |
| Pultakandi | 13 | 09 | 22 | 13 | 09 | 22 | - |  |
| M.F. Alam | 05 | 13 | 18 | 05 | 13 | 18 | - |  |
| Soisuti | 08 | 14 | 22 | 08 | 14 | 22 | - |  |
| South Salua | 15 | 08 | 23 | 15 | 08 | 23 | - |  |
| G.T. | 59 | 63 | 122 | 59 | 63 | 122 | - |  |

All of the children who enrolled this year were also enrolled for Primary Terminal Examination 2011.

2.5) No. of refreshers training organized for FPS teachers:

With the aim of increasing capacity of teachers and improving the quality of education of children, CEP has been conducting monthly refreshers training. During the reporting period, 06 refreshers training were conducted against the target of 06.

95% teachers were participated in refreshers. Various topics related to education were discussed in training to improve the teacher’s skill so that they able to provide good lesson.

Table-10: Attendance status of teachers of FPS school in refreshers training.

| Name of month | Target | Achieved | Deviation | Reasons |
| --- | --- | --- | --- | --- |
|  | Refreshers | Pts | Refresher | Pts |  |  |
| Jan | 01 | 24 | 01 | 23 | 01 | Sickness, pregnancy and Seasonal fever |
| Feb | 01 | 24 | 01 | 23 | 01 |  |
| March | 01 | 24 | 01 | 23 | 01 |  |
| April | 01 | 24 | 01 | 23 | 01 |  |
| May | 01 | 24 | 02 | 47 | 03 |  |
| June | 01 | 24 | - | - | - |  |
| Total | 06 | 144 | 06 | 137 | 07 |  |

2.6) No. of Parents meetings organized in FPS:

Monthly meetings with guardians were held to raise their awareness and interest in children education. During the period of January- June 2011, a total of 34 guardian meetings were held against the target of 12. Child rights, importance of education, childcare, health and hygiene were the topics of discussion. Besides, some important agenda also discussed as per local needs.

Although has had a instruction in project proposal to conduct guardian’s meetings quarterly, but to meet with all guardians, class wise monthly meeting is being conducting for formal primary schools. 94% guardians were present in the meeting. Respective supervisor was present in the meetings. The overall attendance and participation of parents were encouraging and satisfactory during reporting period.

Table -11: Attendance of Formal primary schools parents in the monthly parents meeting.

| Name of month | Target | Achievement | Deviation |
| --- | --- | --- | --- |
|  | Meeting | Participants | Meeting | Participants |  |
| Jan | - | - | 05 | 286 |  |
| Feb | - | - | 06 | 269 |  |
| March | 06 | 958 | 06 | 330 |  |
| April | - |  | 06 | 311 |  |
| May | - | - | 06 | 339 |  |
| June | 06 | 954 | 05 | 280 |  |
| Total | 12 | 1912 | 34 | 1815 |  |

2.7) No of SMC Meeting conducted in FPS:

One of main objective of the project is to strengthening the School Managing Committee. According to the government rules and regulations, 06 School Managing Committee have been formed with 12 members. During the reporting period, 24 SMC meeting was held against the target of 12. More meetings have been organized than target which indicates activeness of committee. 77% committee members were presents in meeting and had taken decision in favor of school.

School managing committee played a vital role in during enrolment of students. They are also actively participating in parents meeting to make understand them about the children wellbeing.

Table-12: Attendance of SMC members in monthly SMC meetings (FPS).

| Name of month | Target | Achieve | Deviation |
| --- | --- | --- | --- |
|  | Meeting | Participants | Meeting | Participants |  |
| Jan | - | - | 04 | 37 |  |
| Feb | - | - | 06 | 56 |  |
| March | 06 | 72 | 03 | 30 |  |
| April | - | - | 03 | 28 |  |
| May | - | - | 03 | 29 |  |
| June | 06 | 72 | 05 | 41 |  |
| Total | 12 | 144 | 24 | 221 |  |

RESULT-3

3. Community and Registered Primary School:

Performance of CPS/RPS

There are 25 Registered and Community Primary Schools in the project area that operating by the government. Out of them, CEP Project is providing technical support to ten Registered and Community Primary Schools in the area of capacity building of teachers, awareness building of parents, promote child rights, increasing facilities for students, reduce drop out and activate the SMCs. Teacher shortage is one of the main problems in these schools. As a result students suffer to receive regular lesson. CEP project has also provided Para teachers in absence of regular teacher.

2.1) Nr of children enrolled: In January 2011, a total of 3508 children (1717 boys and 1791 girls) were enrolled in 10 Community and Registered Primary Schools against the target of 2900.

During the reporting period, 180 children (142 boys and 38 girls) were newly admitted and 06 children (03 boys and 03 girls) were dropped out.  At the end of June, 3682 children (1856 boys and 1826 girls) are now continuing.

Table-13: Enrolment of the children in different CPS/RPS

| Name of school | Category | Class - I | Class – II | Class - III | Class - IV | Class - V | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Haji kalu RPS | Boys | 89 | 48 | 36 | 30 | 24 | 227 |
|  | Girls | 64 | 25 | 53 | 26 | 47 | 215 |
|  | Total | 153 | 73 | 89 | 56 | 71 | 442 |
| Parikherper RPS | Boys | 37 | 31 | 32 | 22 | 12 | 134 |
|  | Girls | 39 | 35 | 38 | 28 | 27 | 167 |
|  | Total | 76 | 66 | 70 | 50 | 39 | 301 |
| Akbarnagar RPS. | Boys | 53 | 46 | 30 | 20 | 10 | 159 |
|  | Girls | 37 | 26 | 23 | 32 | 17 | 135 |
|  | Total | 90 | 72 | 53 | 52 | 27 | 294 |
| Nowgaon RPS | Boys | 109 | 37 | 34 | 25 | 18 | 223 |
|  | Girls | 89 | 38 | 31 | 38 | 25 | 221 |
|  | Total | 198 | 75 | 65 | 63 | 43 | 444 |
| Imemerchar CPS | Boys | 60 | 25 | 43 | 54 | 26 | 208 |
|  | Girls | 35 | 25 | 20 | 46 | 36 | 162 |
|  | Total | 95 | 50 | 63 | 100 | 62 | 370 |
| Gusamara CPS | Boys | 64 | 46 | 73 | 34 | 13 | 230 |
|  | Girls | 58 | 48 | 42 | 53 | 27 | 228 |
|  | Total | 122 | 94 | 115 | 87 | 40 | 458 |
| RagunathpurCPS | Boys | 66 | 59 | 53 | 56 | 24 | 258 |
|  | Girls | 62 | 67 | 56 | 65 | 38 | 288 |
|  | Total | 128 | 126 | 109 | 121 | 62 | 546 |
| Kamar Kanda | Boys | 38 | 26 | 27 | 30 | 13 | 134 |
|  | Girls | 28 | 33 | 23 | 34 | 35 | 153 |
|  | Total | 66 | 59 | 50 | 64 | 48 | 287 |
| Raja Kata CPS. | Boys | 22 | 26 | 23 | 32 | 09 | 113 |
|  | Girls | 21 | 14 | 17 | 32 | 10 | 93 |
|  | Total | 43 | 40 | 40 | 64 | 19 | 206 |
| AtkaparaCPS | Boys | 55 | 53 | 29 | 24 | 09 | 170 |
|  | Girls | 45 | 47 | 31 | 26 | 15 | 164 |
|  | Total | 100 | 100 | 60 | 50 | 24 | 334 |
| Total | Boys | 593 | 397 | 381 | 327 | 158 | 1856 |
|  | Girls | 478 | 358 | 333 | 380 | 277 | 1826 |
|  | Total | 1071 | 755 | 714 | 707 | 435 | 3682 |

3.1) % of average attendance:

During January-June 2011, the average attendance was 88% against the target of 86%. Although the average attendance is higher than the target but 01 school, Atkapara CPS was not able to acquire the target. It was found that in the month March 2011, student’s attendance fall abruptly due conflict between the people of the two village and seasonal diseases.

Table-14: Average attendance of student of community and registered Primary school.

| Sl No | Name of school | Monthly attendance | Average | T.A. Attendance |
| --- | --- | --- | --- | --- |
|  |  | Jan | Feb | Mar | Apr | May | Jun |  |  |
| 1 | Haji kalu RPS | 83 | 85 | 87 | 85 | 91 | 84 | 86 | 88% |
| 2 | Parikherper RPS | 84 | 96 | 98 | 93 | 94 | 94 | 93 |  |
| 3 | Akbarnagar RPS | 85 | 85 | 87 | 86 | 87 | 87 | 86 |  |
| 4 | Nowgaon RPS | 96 | 90 | 92 | 92 | 90 | 94 | 92 |  |
| 5 | Imemerchar CPS | 91 | 91 | 91 | 92 | 82 | 85 | 89 |  |
| 6 | Gusamara CPS | 96 | 88 | 90 | 91 | 91 | 89 | 91 |  |
| 7 | RagunathpurCPS | 93 | 97 | 94 | 95 | 95 | 94 | 95 |  |
| 8 | Kamar Kanda CPS | 92 | 95 | 89 | 92 | 86 | 87 | 90 |  |
| 9 | Raja Kata CPS. | 91 | 89 | 90 | 90 | 93 | 91 | 91 |  |
| 10 | AtkaparaCPS | 73 | 85 | 58 | 78 | 65 | 74 | 72 |  |
| Total |  | 88 | 90 | 87 | 89 | 87 | 88 | 88 |  |

3.2) Nr of children attends in terminal examination (I-IV):

1st terminal examination (Class I-IV) was held in May 2011. Project supported 10 Community and Registered Primary Schools participated in this examination along with other schools in this Upazila. School wise performance has been shown in the below table:

Table-15: First Terminal Examination result of CPS & RPS:

| Name of School | Total Student | Total no. of Student participated in the exam | Deviation | Grade – A (80+) No. of Student | Grade – B (60-79) No. of Student | Grade – C (40-59) No. of Student | Grade – D (-40) No. of Student |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Haji kalu RPS | 442 | 425 | 16 | 101 | 109 | 103 | 112 |
| Parikherper RPS | 301 | 284 | 17 | 28 | 98 | 111 | 47 |
| Akbarnagar RPS | 294 | 229 | 65 | 37 | 60 | 79 | 53 |
| Nowgaon RPS | 444 | 399 | 45 | 129 | 126 | 118 | 26 |
| Imemerchar CPS | 370 | 333 | 37 | 115 | 71 | 58 | 89 |
| Gusamara CPS | 458 | 400 | 58 | 46 | 164 | 141 | 49 |
| RagunathpurCPS | 546 | 539 | 07 | 235 | 214 | 48 | 42 |
| Kamar Kanda CPS | 287 | 251 | 36 | 68 | 87 | 71 | 25 |
| Raja Kata CPS. | 206 | 192 | 14 | 32 | 48 | 61 | 51 |
| AtkaparaCPS | 334 | 295 | 39 | 128 | 94 | 38 | 35 |
| Total | 3682 | 3347 | 334 | 919 | 1071 | 828 | 529 |

From the above data, it is revealed us that 91% students were participated in the examination where 27% students acquired grade-A and 32% students acquired grade-B.

Among the schools, the performance of  Akbarnagar RPS and Rajakata CPS were found poor.

3.3) Nr. of children enrolled for Primary Terminal Examination from CPS/RPS (Grade V):

In this year, students from all 10 Community and Registered Primary Schools will be participated in this examination.  A total of 429 students (153 boys and 276 girls) were enrolled for Primary Terminal Examination out of 435.

Table -16: Enrolled students for Primary Terminal Examination for FPS

| Name of the schools | # of student | Nr of students enrolled for exam | Deviation | Remarks |
| --- | --- | --- | --- | --- |
|  | B | G | T | B | G | T |  |  |
| Haji kalu RPS | 24 | 47 | 71 | 24 | 47 | 71 | - |  |
| Parikherper RPS | 12 | 27 | 39 | 13 | 26 | 39 | - |  |
| Akbarnagar RPS | 10 | 17 | 27 | 10 | 16 | 26 | 01 |  |
| Nowgaon RPS | 18 | 25 | 43 | 17 | 26 | 43 | - |  |
| Imemerchar CPS | 26 | 36 | 62 | 25 | 35 | 60 | 02 |  |
| Gusamara CPS | 13 | 27 | 40 | 13 | 27 | 40 | - |  |
| RagunathpurCPS | 24 | 38 | 62 | 24 | 38 | 62 | - |  |
| Kamar Kanda CPS | 13 | 35 | 48 | 13 | 35 | 48 | - |  |
| Raja Kata CPS. | 09 | 10 | 19 | 09 | 10 | 19 | - |  |
| AtkaparaCPS | 09 | 15 | 24 | 05 | 19 | 21 | 03 |  |
| G.T. | 158 | 277 | 435 | 153 | 276 | 429 | 06 |  |

3.4)  No. of refreshers training organized for CPS/RPS teachers:

According to the plan, 03 refreshers meeting supposed to organize by the project in 2011. During reporting period, 01 refreshers training were provided for community and registered primary school teachers against the target of 01. Rest 02 refreshers will be organized within the next half.

Attendance of CPS and RPS teachers in refresher training is presented in the table below:-

Table-17.  Attendance of teachers in refreshers training.

| Name of month | Participants | Remarks |
| --- | --- | --- |
|  | Target Nr of meetings/Participants | Achieve Nr of meetings/Participants | Deviation |  |
| March | 01/50 | 01/49 | 01 | Due to sickness. |

3.5) No. of Parents meetings organized in CPS/RPS:

According to the plan, quarterly parents meeting to be conduct in Registered and Community Primary Schools during the reporting period. A total of 45 parents meeting were organized by these schools during January to June 2011 against the target of 20. 25 more meetings were organized by the schools as per their need. Monthly parents meetings are being held to raise their awareness and interest. In the meeting, child rights, importance of education, child labor and child healthcare are discussed. The Project Coordinator and Supervisor were present in the meeting. Month wise attendance of Community and Register primary schools parents is presented in the table below:-

Table-18:    Attendance of CPS /RPS primary schools parents in the monthly parents meeting.

| Month | Target | Achieve | Remarks |
| --- | --- | --- | --- |
|  | No of meetings | Participants | No of meetings | Participants |  |
| January | - | - | 10 | 766 |  |
| Feb | - | - | 07 | 356 |  |
| March | 10 | 3508 | 08 | 365 |  |
| April | - | - | 10 | 531 |  |
| May | - | - | 10 | 472 |  |
| June | 10 | 3682 | 10 | 461 |  |

80% guardians were participated in the monthly parent meeting.

3.6) No of SMC meeting conducted in CPS/RPS:

SMC members can play a vital role to improve the school performance. But the real scenario is not so good in Bangladesh. Most of the SMCs of schools are not functioning properly. Schools under CEP Project have been trying to active these SMCs in favor of schools quarterly. One of the main activities is to conduct SMC meeting in schools. During the reporting period, January- June 2011, 60 SMC meetings were organized by the Registered and Community Primary Schools against the target of 20.

On an average 74% SMC members were present in the meetings.

Table-19:    Attendance of SMC members in monthly SMC’s meetings (CPS /RPS).

| Month | Target | Achievement | Remarks |
| --- | --- | --- | --- |
|  | No of meetings | Participants | No of meetings | Participants |  |
| January | - | - | 10 | 95 |  |
| February | - | - | 10 | 88 |  |
| March | 10 | 120 | 10 | 88 |  |
| April | - | - | 10 | 90 |  |
| May | - | - | 10 | 85 |  |
| June | 10 | 120 | 10 | 89 |  |
| Total | 20 | 240 | 60 | 535 |  |

3.7) No. of SMC members trained of Child Rights:

One of the main objectives of the project is to promote the child rights according to the UNCRC. With the aim of increasing capacity and awareness among the SMC members, CEP Project has been organized training for SMC members. According to the plan, two workshops about child rights were supposed to organize in each year for the SMC members of Formal primary School and Community & Registered Primary School.

First workshop was held on 15th and 16th May 2011 for the members of Community & Registered Primary school. A total of 30 SMC members from 04 Community and Registered Primary Schools were participated in the workshop against the target of 30.

RESULT-4

4. Orphanage

Performance of Orphanage:

Activities of Orphanage are conducted to improve health, education and behavior of 44 children. The children have been studying different grade in schools. Orphan children are receiving general education with religious education at morning. Orphan children are organized into three age groups. 4-5 years old are in pre-school groups, 6-11 years old orphans are in primary school group and 12-18 years old orphans are in high school group.

Each orphan is supplied with clean bed, mosquito net, bed sheet, pillow with cover, three times full meals regularly. In addition to these orphans enjoy use of adequate sanitary latrines, safe water facilities, clean and sanitized environment of dwelling dormitory and fresh air. Children have opportunities to play games at field in front of the orphanage daily. These contribute a lot to orphan to keep in good health.

4.1) No of children enrolled in Orphanage:

During the reporting period, a total of 54 boys were getting educational support from the orphanage who was admitted in different class in the local institutions. Information about enrolment of orphan boys was given in below tables.

Table-20:  Children information of orphanage

| Kinds of school | Class |
| --- | --- |
|  | Pre-Primary | Total |
| ECD | 02 | 02 |

| Kinds of school | Class |
| --- | --- |
|  | Class-I | Class-II | Class-III | Class-IV | Class-V | Total |
| Primary | 08 | 05 | 02 | 09 | 03 | 27 |

| Kinds of school | Class |
| --- | --- |
|  | Class-VI | Class-VII | Class-VIII | Class-IX | Class-X | Total |
| Secondary | 01 | 03 | 02 | 02 | 07 | 15 |

4.2) Nr of children completed Secondary Education:

In February 2011, secondary examination was held throughout the country where 02 boys from orphanage were participated in the examination. Both of them passed successfully.

4.3) No of children Enrolled for Primary Terminal Examination:

03 boys of class-V of orphanage are now studying in Pultakandi Formal Primary Schools. They will sit for Primary Terminal Examination-2011 and have been enrolled for examination.

5.  Project monitoring:

Project has been introduced quantitative and qualitative monitoring for improvement quality of schools. Project Coordinator and supervisor continuously make their supervision and monitoring the schools for ensuring quality of teaching, improve student’s performance and effective role play of the SMC members. Besides, focal person of the project and donor organization also monitor the project activities routinely.

Monitoring by Donor: In March (1st-3rd), 2011, project was visited by the Coordinator of TdH-NL Dhaka office. After monitoring the project he has given some recommendations for better performance the program. His findings and recommendations are as given below:-

- Should have to improve the knowledge of the teachers.

- Have to change C.I sheets of Pultakandi FPS.

- To make ceiling of roof in the formal primary schools.

Some action has been taken against the recommendations, these are,

  - All teachers of ECD have been trained up to improve their knowledge. In field visit, supervisors are also providing support according to their needs.

  - C.I. sheets of Pultakandi FPS have already been changed.

  - Ceiling of the roofs of all schools are being made gradually.

Monitoring by Project Focal Person: Mr. Mujibor Rahman, Director of POPI and Focal Person of CEP Project has visited the project on 7th -8th June 2011. During his visit in South Salua Formal Primary school, he discussed with the teachers and checked the registers. He gave suggestions to keep records up date. He also discussed with the chairperson of SMC about to construct the floor by collecting fund from community.

He also visited a Community Primary School (Fariroghunathpur CPS) to oversee the newly constructed ECD center. He discussed with Head Master Mrs. Monira Begum about the support from the project. Head Master explained how the project contribution helps to improve the performance. She also thanks to support by appoint the para-teachers from the project which helps a lot against the shortage of teachers. It is mentionable that 544 children are now studying in this community school with only 03 government teachers.

Chapter-3

1.  Conclusion:

During the reporting period, some observations about project activities are stated below:

Staff Development: Project provides in service training to its staff members. During January - June 2011, CEP Project organized training for its staffs that conducted by VERC and POPI.

- 2-days long follow up training for 20 ECD teachers and 01 supervisor on Early Learning.

- 2-days long follow up training for 23 Primary teachers and 01 supervisor on Primary Education.

- 2-days long follow up training for 2 supervisors on Primary Education.

- 2-days long follow up training for 1 Project Coordinator on Child Rights.

- 2-days long workshop for 1 Project Coordinator on Advocacy.

- 3-days long follow up training for 1 Project Coordinator on Logical Framework.

- 2-days long workshop for 1 Project Coordinator and 1 supervisor on Child Protection Policy.

Teacher Drop out: During the reporting period 13 staffs were dropped out from the project due to various reasons. Among the components, drop out rate of Para-teacher from Community and Registered Primary Schools was high than the other component. Component wise drop out information are as given below:

| Components | Nr of Teacher/ para-teacher drop out | Reasons |
| --- | --- | --- |
| Early Child Development | 04 | All for marriage. |
| Formal Primary School | 01 | Got job opportunity in high school. |
| Community and Registered Primary School | 06 | Less interest for this job. |
| Orphan Staff | 02 | Got better job opportunity |
| Total | 13 |  |

Overall Objectives:

- Children have access to education: During the reporting period, 5300 children have accessed to education against the target of 4455.

- People aware of child rights: 4395 children have been aware about the Child Rights through parents meeting against the target of 4448.