Activity Monitoring Report

Of

Children Education Program (CEP)

Period: January to June, 2010

Submitted to: TDH-Netherlands.

Submitted By:

POPI

People’s Oriented Program Implementation

5/11-A,Block-E,Lalmatia,Dhaka-1207

E-mail: popi@bdmail.net;

Website: www.popibd.org

Table of Contents

Page No.

Chapter-1 			3

- Background information			3

- Results 			3

- Summary of the activity monitoring report			6

Chapter-2			7

Detail accounts of activities			7

- Early Child Development (ECD) 			7

- Formal Primary Schools			8

- Community and Register Primary School			12

- Orphanage			15

- Project monitoring			15

- Achievement against target                                                                     17

- Lesson learned                                                                                        19

Chapter-3			20

1. Conclusion			20

Chapter-1

1. Background information:

The report of the program is the Activity Monitoring Report (period January to June,2010) of the CEP Program. The program has gone through 6th phase of implementation. The report reflects activities performance against expected results and achievement of purpose of the program in the reporting period. Under the program, children of the poor and extremely poor families are targeted, where there was no school to impart quality education. The specific objective is to children rights promotion in project area and purpose of the program is establishment of universal primary education for the deprived children of the projects areas.

To reach the aforesaid aim, 4 specific results are expected to be achieved at the end of project period. The Activity monitoring has been conducted through participatory process by  involving beneficiaries, stakeholders and personnel’s of the project. At the beginning of the project, number of tools were introduced to keep record of accomplishment i.e. attendance register, meeting minutes of SMC, exam’s score compilation sheets. That information are being collected and collated to generate this report. The expected results of the project are as follows;

2. Results:

| Results qualitative | Results quantitative(indicators) |
| --- | --- |
| 1. Children have access Early Childhood Development (ECD) program. | 1.1.1 ) No. of ECD centers established Year-1 Year 2 Year 3 20 20 20 1.1.2) No. of children enrolled Year-1 Year 2 Year 3 600 600 600 1.1.3) Drop out rate reduced Year-1 Year 2 Year 3 03 02 01 1.1.4) Percentage of average attendance of children increased Year-1 Year 2 Year 3 97% 97% 98% 1.1.5) No. of trained teachers on ECD Year-1 Year 2 Year 3 20 20 20 1.1.6) No. of participants aware of child rights through parents teachers meeting Year-1 Year 2 Year 3 600 600 600 |
| 2. Children have access to primary education organized by POPI. | 1.2.1) No. of Primary School establishment Year-1 Year 2 Year 3 06 06 06 1.2.2) No. of children enrolled Year-1 Year 2 Year 3 900 900 900 1.2.3) Rate of dropout reduced Year-1 Year 2 Year 3 04 3.5 3 1.2.4) Percentage of average children attendance increased Year-1 Year 2 Year 3 96% 97% 97% 1.2.5) No. of trained teacher on primary education Year-1 Year 2 Year 3 24 24 24 |
| 3. Children have access to community and registered primary schools | 1.3.1) No. of Community and registered Primary School supported Year-1 Year 2 Year 3 10 10 10 1.3.2) No. of children enrolled Year-1 Year 2 Year 3 2900 2900 2900 1.3.3) Rate of dropout reduced Year-1 Year 2 Year 3 15 13 10 1.3.4) Percentage of average children attendance increased Year-1 Year 2 Year 3 85% 86% 87% 1.3.5) No. of children promoted to next class Year-1 Year 2 Year 3 2900 2900 2900 1.3.6 No. of children promoted primary school (grade V) Year-1 Year 2 Year 3 340 345 350 1.3.7) No. of trained teacher on primary education Year-1 Year 2 Year 3 50 50 50 1.3.8) No. of participants aware of child rights through quarterly parents teacher meeting Year-1 Year 2 Year 3 2900 2900 2900 1.3.9) No. of SMC members trained on child rights Year-1 Year 2 Year 3 30 30 30 |
| 4. Orphan children have access to education | 1.4.1) No. of children enrolled in orphanage Year-1 Year 2 Year 3 55 55 55 1.4.2) No. of children enrolled in primary school Year-1 Year 2 Year 3 22 22 22 1.4.3) No. of children enrolled in secondary school Year-1 Year 2 Year 3 33 33 33 1.4.4) No. of school children promoted to next classes Year-1 Year 2 Year 3 55 55 55 1.4.5) No. of children completed primary school (grade-5) Year-1 Year 2 Year 3 1 5 8 1.4.6) No. of children completed secondary school Year-1 Year 2 Year 3 3 5 8 1.4.7) No. of children received shelter, food and non-food items Year-1 Year 2 Year 3 55 55 55 |

3. Summary of the Activity monitoring Report:

The Activity monitoring report is sum of information and facts those were recorded by weekly and monthly monitoring of teachers and project staff including project coordinator during the reporting period.

- As planned, 20 ECD center were established and 665 (actual target was 600) children of age 5-6 years are getting early childhood education (nursery education) at the ECD centers. They are belong to the poor and extreme household and getting preschool nursery curriculum through playing with games materials toys , sticks, seeds, etc. ECD education frame pro-school mindset of children and erase fear of studies and grow interest to go to schools.

- 937 (targeted 900) children of age 6-15 years are receiving formal primary education through government curriculum activities in 6 Formal Primary Schools (one is for Dalit children in Bhairab municipality).

- 3153 (targeted 2900) children of 10 community and registered primary school are receiving support ( training to teachers, partly salary of teachers, furniture , water and sanitation facilities for children )  to enhance quality education for children.

- One orphanage is maintained where 55 orphan (boys) are getting supports  for education in different classes, health care, food subsidy, house tutor, private tutors, education materials, games, sports and cultural teaching.

- To enhance quality education community people are involved in SMC, parents are involved in regular meetings. Coordination and cooperation are established with government education department and local administration. Local elected bodies extending voluntary support with cash and kind. The quality of education in these schools is better that marked from the children attendance rate and performances in the last examination.

- Two formal primary schools received1st letter during 2009. This year we are waiting for 2nd letter. Three formal school registrations are in process. Application for registration of one school yet to be submitted because of some complicacy with land donation.

- Orphanage Children had been participated in the Inter-school Football Tournament and Cricket Tournament as well. In both the tournaments, Orphanage team won the championship trophy.

- Staff and teacher turnover was a bit high. During reporting period, PC (in the middle of June) and 6 ECD teachers and 2 teachers from formal school left job.

Chapter-2:

DETAIL ACCOUNTS OF ACTIVITIES PERFORMANCES.

1. Early Child Development

1.1 Performances of ECD:

At the beginning of the year 2010, 20 ECDs with 665 learners were established. Locations of 16 ECD centers are located in same places where those were during 5th phase of the program. Four ECD centers were established in 4 new locations. Community people gave spontaneous support (cash/kind/physical labour) in construction of new centers and renovation of old ECD centers.

During the reporting period, there was no dropout of children.

Teaching materials developed by the teachers are getting popularity among the new learners aslo. Children have been demonstrating continuous interest in the learning sessions.

Average attendance of children was 97% (Jan-June’10). Attendance of children at each ECD centre is presented in the table below-

Table-1: Average monthly attendance of ECD centers.

| Sl No | Name of school | Monthly attendance | Average | All average % |
| --- | --- | --- | --- | --- |
|  |  | Jan | Feb | March | April | May | June |  |  |
| 1 | Mirerchar (FPS) | 98 | 99 | 99 | 98 | 99 | 99 | 99 | 97% |
| 2 | Pultakandi (FPS) | 96 | 98 | 98 | 98 | 99 | 99 | 98 |  |
| 3 | Mohammad Ali (FPS) | 99 | 98 | 99 | 98 | 98 | 95 | 98 |  |
| 4 | Mohammad Ali (FPS) | 96 | 96 | 99 | 98 | 96 | 92 | 95 |  |
| 5 | Faisul Alam Pathshala (FPS) | 98 | 98 | 99 | 97 | 99 | 98 | 98 |  |
| 6 | Choto Soisuti (FPS) | 99 | 96 | 98 | 97 | 98 | 97 | 98 |  |
| 7 | South Salua (FPS) | 97 | 97 | 97 | 96 | 99 | 97 | 97 |  |
| 8 | Haji Kalu Miah RPS | 96 | 97 | 99 | 97 | 97 | 97 | 97 |  |
| 9 | Akbar Nagar RPS | 97 | 97 | 97 | 96 | 97 | 95 | 97 |  |
| 10 | Porikharpar RPS | 95 | 95 | 96 | 95 | 95 | 95 | 95 |  |
| 11 | Naogaon RPS | 95 | 90 | 97 | 98 | 92 | 95 | 95 |  |
| 12 | Imamer Char (CPS) | 97 | 98 | 98 | 98 | 98 | 98 | 98 |  |
| 13 | Imamer Char (CPS) | 98 | 99 | 97 | 97 | 97 | 97 | 98 |  |
| 14 | Gochamara (CPS) | 97 | 97 | 98 | 97 | 98 | 98 | 98 |  |
| 15 | Gochamara (CPS) | 93 | 95 | 96 | 96 | 97 | 95 | 95 |  |
| 16 | Fari Ragunathpur (CPS) | 94 | 94 | 99 | 99 | 99 | 99 | 97 |  |
| 17 | Fari Ragunathpur (CPS) | 94 | 98 | 99 | 99 | 99 | 97 | 98 |  |
| 18 | Kamarkanda (CPS) | 97 | 96 | 98 | 98 | 98 | 98 | 98 |  |
| 19 | Chotorajakata (CPS) | 96 | 96 | 97 | 97 | 96 | 97 | 97 |  |
| 20 | Atkapara (CPS) | 92 | 99 | 99 | 97 | 98 | 97 | 97 |  |
| Total |  | 96 | 97 | 98 | 97 | 97 | 97 | 97 |  |

From the above table, it is observed that attendance rate of children at 4 centers (Mohammadli FPS, Porikharpa RPS, Nowgaon RPS and Gochamara CPS) are comparatively low (95%) than that of other ECD centers. Reasons for low attendance are as follows:

- Sickness

- Visit relatives with mothers

- Excessive rain

- Father’s / mothers illness

- Closing of Primary School where elder siblings didn’t come to school

1.2 Refreshers training for ECD teachers:

During the reporting period Jan to June’ 2010, six refresher training were organized. Average 19 teachers out of 20 received the training. Main reason of absent in the refresher training was sickness and resigned from service. During reporting period, total 6 teachers resigned. New teachers were recruited against vacant position. It was not possible to provide basic training to the two newly recruited teacher because of budget constraint. However, they have been given on the job training by the Project Coordinator, and Supervisor. They also participated in the refresher training of May and June. In the refresher trainings five important topics were facilitated. Teachers who are new and comparatively weak, they were given more emphasis to role play on different learning method and materials. Teachers enjoyed methods of the training e.g. role play, Rhyme recitation). As a whole, refreshers enriched their knowledge and skills on the quality of curriculum delivery and method and technique of classroom activities. Because of refresher training, teachers demonstrate better performance in the class. Month wise teacher’s attendance in monthly review and refreshers trainings is presented below:-

Table -2: Attendance of teachers in monthly refreshers training.

| Name of month | Target | Achieved | Deviation | Remarks |
| --- | --- | --- | --- | --- |
|  | Refreshers | Pts | Refresher | Pts |  |  |
| Jan | 1 | 20 | 1 | 19 | 1 |  |
| Feb | 1 | 20 | 1 | 19 | 1 |  |
| March | 1 | 20 | 1 | 19 | 1 |  |
| April | 1 | 20 | 1 | 19 | 1 |  |
| May | 1 | 20 | 1 | 18 | 2 |  |
| June | 1 | 20 | 1 | 20 | - |  |

2. Formal Primary Schools (POPI Managed):

There are six Formal Primary Schools established and managed by POPI with the support from TDH-N. Two school already received 1st letter for registration in 2009 and likely to receive 2nd letter soon. Registration application for 3 schools is under process. Rest one school (Faisal Alam Smriti Patshala) registration process kept pending because of land tenure complicacy. This school situated on the Government Khash land. On behalf of the community, Mayor already applied for permanent lease from the Govt.

Community contribution (cash/kind) continues. Mohammad Ali School, land donor and president of the school constructed 1 pucca latrine and installed one tubewell with pucca platform.

All 24 teachers were trained. After conduction of training, 1 teacher resigned and it was not possible to provide her basic training.

…..

  - Student enrolled: Total 937 students (almost 50% girls – 468 and 50% boys 469 ) enrolled      in the 6 Formal Primary Schools. Information of student enrolled is presented in table -3.

Table-3:  Information of student enrolled.

| Name of school | One | Two | Three | Four | Five | Grand total |
| --- | --- | --- | --- | --- | --- | --- |
|  | B | G | T | B | G | T | B | G | T | B | G | T | B | G | T | B | G | T |
| Mirerchar | 22 | 13 | 35 | 32 | 38 | 70 | 19 | 16 | 35 | 13 | 17 | 30 | 18 | 12 | 30 | 104 | 96 | 200 |
| Mohammad Ali | 20 | 18 | 38 | 14 | 09 | 23 | 07 | 14 | 21 | 07 | 03 | 10 | 03 | 01 | 04 | 51 | 45 | 96 |
| Pultakandi | 18 | 12 | 30 | 17 | 13 | 30 | 16 | 13 | 29 | 16 | 13 | 29 | 15 | 15 | 30 | 82 | 66 | 148 |
| Faisal Alam | 14 | 16 | 30 | 22 | 08 | 30 | 13 | 17 | 30 | 12 | 17 | 29 | 06 | 24 | 30 | 67 | 82 | 149 |
| S.Salua | 24 | 21 | 45 | 20 | 20 | 40 | 14 | 26 | 40 | 25 | 10 | 35 | 09 | 20 | 29 | 92 | 97 | 189 |
| Soisuti | 17 | 18 | 35 | 14 | 16 | 30 | 14 | 16 | 30 | 13 | 17 | 30 | 15 | 15 | 30 | 73 | 82 | 155 |
| Total | 115 | 98 | 213 | 119 | 104 | 223 | 83 | 102 | 185 | 86 | 77 | 163 | 66 | 87 | 153 | 469 | 468 | 937 |

  - Monthly attendance:

Attendance of student in Formal primary schools is comparatively better than that of government schools in the area. In government primary school average attendance vary from 75% to 80% (CPS, RPS attendance 87%), but average attendance of student in Formal primary schools is 97%.

Month wise student attendance is presented in the table below:

Table -4: Month wise student attendance of each school (FPS):

| Sl No | Name of school | Monthly attendance | Average | T.A. Attendance |
| --- | --- | --- | --- | --- |
|  |  | Jan | Feb | March | April | May | June |  |  |
| 1 | Mirerchar | 98 | 99 | 98 | 99 | 98 | 98 | 98 | 97% |
| 2 | Pultakandi | 98 | 99 | 98 | 98 | 98 | 98 | 98 |  |
| 3 | Mohammad Ali | 82 | 95 | 99 | 98 | 98 | 97 | 95 |  |
| 4 | Faisal Alam | 98 | 98 | 98 | 98 | 98 | 97 | 98 |  |
| 5 | Choto Soisuti | 96 | 96 | 95 | 97 | 97 | 97 | 96 |  |
| 6 | South Salua | 97 | 96 | 95 | 96 | 95 | 96 | 96 |  |

  - 1st terminal exam’s result:

National curriculum of text book (NCTB) is followed to teach same standards in all schools. Teachers performance evaluate regularly through monitoring visit.  Students’ weekly and monthly tutorial examinations held regularly. Records of results of those exams are preserved at each school. First terminal examinations of all schools held at examination centre arranged by upazila primary education department. Result of the examination was declared and student of formal primary schools did better performances except one School.  South Salua School student’s participation and result is below requirement. The reason of poor performance of this school has identified that this school situated in haor area and during rice harvesting time, 1st terminal exam was held. At that many student were involved with rice harvesting and processing. They were less attentative to study and some parents were reluctant to participation of their children in the exam. Information of 1st terminal exam is presented in table -5 below:-

Table-5: First terminal exam result of Formal Primary school :

| Name of School | Total Student | Total no. of Student participated in the exam | Deviation | Grade – A (80+) No. of Student | Grade – B (60-79) No. of Student | Grade – C (40-59) No. of Student | Grade – D (-40) No. of Student |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mirarchar | 200 | 200 | - | 96 | 86 | 13 | 05 |
| Mohammad Ali | 96 | 96 | - | 44 | 22 | 13 | 17 |
| Pultakandi | 150 | 150 | - | 13 | 31 | 97 | 09 |
| Faisal Alam | 150 | 150 | - | 36 | 65 | 38 | 11 |
| South Salua | 189 | 150 | 39 | 33 | 19 | 34 | 64 |
| Soisuti | 155 | 155 | - | 44 | 71 | 29 | 11 |
| Total | 940 | 901 | 39 | 266 | 294 | 224 | 117 |

2.4 . Refreshers training (FPS):

There are six refreshers trainings (one in each month) held during the reporting period  for the teachers of Formal primary schools (POPI managed). The target of refreshers training is fulfilled. It was targeted to provide training to all the 24 teachers but teacher’s presence in the training varies in month to month. In the month of March and May all 24 teachers attended the training but in other months 1-2 teachers remained absent from attending refreshers courses. In January and June, 1 teacher in each refresher training was absent due to sickness. In February and April, 2 teachers and 1 teacher’s position was remained vacant. There was no change or deviation in courses delivery or procedure during the reporting period. Refreshers training was smoothly done.

Attendance of teachers in the refreshers training is presented in the table below-

Table-6:    Attendance status of teachers in formal primary school refreshers training.

| Name of month | Target | Achieved | Deviation | Remarks |
| --- | --- | --- | --- | --- |
|  | Refreshers | Pts | Refresher | Pts |  |  |
| Jan | 1 | 24 | 1 | 23 | 1 |  |
| Feb | 1 | 24 | 1 | 22 | 2 |  |
| March | 1 | 24 | 1 | 24 | - |  |
| April | 1 | 24 | 1 | 23 | 1 |  |
| May | 1 | 24 | 1 | 24 | - |  |
| June | 1 | 24 | 1 | 23 | 1 |  |

2.5   Formal primary school parents meeting: According to student enrollment 937 parents are targeted to participate in parents meeting per month. Actual attendance of parents was very low than target. The reason for less parents from the target is because there are more than one child of a parent has been admitted into the formal primary schools. In each month, it was targeted to hold 6 meeting (1 in each school), but in Jan and Feb 4 meetings per month was held against 6. Parents regretted to participate in the meeting monthly. Rather, they proposed to hold meeting quarterly. In compliance with the parent’s proposal, since April’10 parents meeting had been conducting targeting 2 classes parents in every month i.e. 1st month class 1+3, 2nd month class 2+4 and 3rd month class 5+1. During the quarter April-June, 889 out of 937 parents were participated in the meeting.

Table -7: Attendance of Formal primary schools parents in the monthly parents meeting.

| Name of month | Target | Achievement | Deviation |
| --- | --- | --- | --- |
|  | Meeting | Participants | Meeting | Participants |  |
| Jan | 6 | 937 | 4 | 206 |  |
| Feb | 6 | 937 | 4 | 172 |  |
| March | 6 | 937 | 5 | 207 |  |
| April | 6 | 360 | 6 | 303 |  |
| May | 6 | 360 | 6 | 301 |  |
| June | 6 | 360 | 6 | 285 |  |
| Total | 36 | 3909 | 31 | 1525 |  |

2.6. SMC Meeting:

In each school there was SMC committee consisting 11 members except Mohammad Ali School. SMC was newly formed in Mohammad Ali School in March’09 as this School was established in Jan’10. It was targeted to hold SMC meeting at each school on monthly basis and total 36 SMC meetings in six months.  During the reporting period, total 30 meetings were held instead of 36.  Mirarchar and Fultakandi School’s SMC  members dropped two monthly meetings. It was not possible to hold 3 SMC meetings in Mohammad Ali School because at this school full SMC was formed in March’10. However, at Mohammad Ali School there were several meetings with the community at the beginning stage of the school establishment. Until March SMC was consisting 11 members, later on Govt. introduced 12 members SMC at Govt. School. In compliance with the Govt., 12 members SMC were formed in 4 schools and another two school yet to be reform by 12 members SMC.

Table-8: Attendance of SMC members in monthly SMC’s meetings (FPS).

| Name of month | Target | Achieve | Deviation |
| --- | --- | --- | --- |
|  | Meeting | Participants | Meeting | Participants |  |
| Jan | 6 | 66 | 5 | 47 | 1 |
| Feb | 6 | 66 | 3 | 30 | 3 |
| March | 6 | 66 | 4 | 32 | 2 |
| April | 6 | 77 | 6 | 57 | - |
| May | 6 | 77 | 6 | 58 | - |
| June | 6 | 77 | 6 | 58 | - |
| total | 36 | 408 | 30 | 362 |  |

2.7. Parents and community contribution:

After satisfaction of student’s results and management of FPS a good number of parents and community people contributed for schools in term of cash and kind contributions are presented school wise in the table below: (Contributions are calculated up-to 30 June 2010)

Table-9:    Particulars of parents and community contribution.

| Name of school | Target | # of student | # of family | # of contributed family | Others contributor | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Mirerchar |  | 200 | 185 | 185 | 10 | 195 |
| Pultakandi |  | 148 | 132 | 132 | 31 | 163 |
| Mohammad Ali |  | 96 | 81 | 81 | 27 | 108 |
| Rabidaspara |  | 149 | 128 | 128 | 18 | 146 |
| Soisuti |  | 155 | 137 | 137 | 15 | 152 |
| S.Salua |  | 189 | 172 | 172 | 1 | 183 |
| Sub-total |  | 937 | 835 | 835 | 112 | 947 |
| Ten ECD in CPS/RPS |  |  |  |  |  |  |
| G.T |  |  |  |  |  |  |

3.   Community and registered Primary School

3.1  Total 3153 students enrolled in 10 Community and  Registered Schools where Girl 1595 and boys 1558. Student information is shown in Table 9:

Table-10: student information of community & registered Primary schools.

| Name of school | One | Two | Three | Four | Five | Grand total |
| --- | --- | --- | --- | --- | --- | --- |
|  | B | G | T | B | G | T | B | G | T | B | G | T | B | G | T | B | G | T |
| Nowgaon | 55 | 50 | 105 | 31 | 52 | 83 | 29 | 46 | 75 | 23 | 23 | 46 | 05 | 22 | 27 | 143 | 193 | 336 |
| Haji Kalu | 49 | 26 | 75 | 28 | 22 | 50 | 34 | 29 | 63 | 29 | 57 | 86 | 23 | 23 | 46 | 163 | 157 | 320 |
| Akbar Nagar | 45 | 34 | 79 | 27 | 19 | 46 | 17 | 32 | 49 | 12 | 23 | 35 | 06 | 13 | 19 | 107 | 121 | 228 |
| Parikharpar | 35 | 40 | 75 | 36 | 29 | 65 | 32 | 32 | 62 | 21 | 35 | 56 | 08 | 21 | 29 | 130 | 157 | 287 |
| Atkapara | 54 | 46 | 100 | 55 | 45 | 100 | 42 | 28 | 70 | 30 | 27 | 57 | 13 | 10 | 23 | 194 | 156 | 350 |
| Gochamara | 46 | 43 | 89 | 40 | 33 | 73 | 60 | 42 | 102 | 28 | 47 | 75 | 21 | 39 | 60 | 195 | 204 | 399 |
| Imamerchar | 39 | 29 | 67 | 40 | 22 | 62 | 51 | 32 | 83 | 27 | 30 | 57 | 20 | 20 | 40 | 176 | 133 | 309 |
| Pari Ragunathpur | 58 | 71 | 129 | 61 | 56 | 117 | 57 | 64 | 121 | 26 | 42 | 68 | 22 | 25 | 47 | 224 | 258 | 482 |
| Kamarkanda | 31 | 29 | 60 | 25 | 25 | 50 | 30 | 29 | 59 | 27 | 31 | 58 | 17 | 28 | 45 | 130 | 142 | 272 |
| Rajakata | 25 | 09 | 34 | 18 | 15 | 33 | 27 | 19 | 46 | 17 | 20 | 37 | 09 | 11 | 20 | 96 | 74 | 170 |
| Total | 436 | 377 | 813 | 361 | 318 | 679 | 377 | 353 | 730 | 240 | 335 | 575 | 144 | 212 | 356 | 1558 | 1595 | 3153 |

3.2:  Average attendance is 87% quite better than other Govt. registered school. School wise attendance rate is shown in table 10.

Table-11: Average attendance of student of community and registered Primary school.

| Sl No | Name of school | Monthly attendance | Average | T.A. Attendance |
| --- | --- | --- | --- | --- |
|  |  | Jan: | Feb: | March | April | May | June |  |  |
| 1 | Haji kalu RPS | 88 | 82 | 89 | 91 | 87 | 87 | 87 | 87% |
| 2 | Parikherper RPS | 87 | 88 | 88 | 92 | 80 | 88 | 87 |  |
| 3 | Akbarnagar RPS | 91 | 84 | 81 | 84 | 86 | 88 | 86 |  |
| 4 | Nowgaon RPS | 85 | 91 | 90 | 88 | 76 | 88 | 86 |  |
| 5 | Imemerchar CPS | 84 | 92 | 93 | 92 | 91 | 90 | 90 |  |
| 6 | Gusamara CPS | 80 | 84 | 85 | 88 | 83 | 82 | 84 |  |
| 7 | RagunathpurCPS | 87 | 91 | 92 | 91 | 91 | 85 | 90 |  |
| 8 | Kamar Kanda CPS | 87 | 92 | 89 | 96 | 90 | 90 | 91 |  |
| 9 | Raja Kata CPS. | 91 | 87 | 83 | 86 | 81 | 82 | 85 |  |
| 10 | AtkaparaCPS | 85 | 82 | 83 | 77 | 83 | 84 | 82 |  |
| Total |  | 87% | 87% | 87% | 89% | 85% | 86% | 87% |  |

3.3    Class wise student result of CPS and RPS.

Class wise results of 1st terminal Examinations of boys and girls of CPS and RPS are

presented in the table below:-

Table-12:  1st terminal results of CPS & RPS:

| Name of School | Total Student | Total no. of Student participated in the exam | Deviation | Grade – A (80+) No. of Student | Grade – B (60-79) No. of Student | Grade – C (40-59) No. of Student | Grade – D (-40) No. of Student |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Nowgaon | 336 | 304 | 32 | 65 | 88 | 63 | 88 |
| Haji Kalu | 320 | 317 | 03 | 74 | 83 | 105 | 55 |
| Akbar Nagar | 220 | 191 | 29 | 37 | 57 | 56 | 41 |
| Parikharpar | 287 | 261 | 26 | 32 | 50 | 111 | 68 |
| Atkapara | 350 | 235 | 115 | 96 | 86 | 27 | 26 |
| Gochamara | 399 | 392 | 07 | 78 | 199 | 57 | 58 |
| Imamerchar | 309 | 288 | 21 | 85 | 70 | 54 | 79 |
| Pari Ragunathpur | 482 | 445 | 37 | 66 | 174 | 168 | 37 |
| Kamarkanda | 272 | 262 | 10 | 49 | 45 | 116 | 52 |
| Rajakata | 170 | 157 | 13 | 31 | 63 | 39 | 24 |
| Total | 3145 | 2852 | 293 | 613 | 915 | 796 | 528 |

3.4   Refresher training for teachers of community and registered primary schools:

Target of refreshers training for community and registered primary school was 1 training in 3 month’s interval and it was held at education office in March’10. Total 48 teachers were participated. Two teachers couldn’t participate because of other Govt. assigned business.

Attendance of CPS and RPS teachers in refresher training is presented in the table below:-

Table-13: Month wise attendance of community and registered school teachers in refreshers training.

| Name of month | Target of training | Target pts | Achieve | Deviation | Remarks |
| --- | --- | --- | --- | --- | --- |
| March | 1 | 50 | 48 | 2 | Meeting in Education Office |

3.5 . Community registered primary schools parents meetings:

Parent’s meeting was targeted one meeting in each school per month. Total 60 meeting was supposed to hold at 10 Community and registered schools. But total 44 parents meeting held. Parents are not willing to sit for meeting every month and parents meeting couldn’t possible to hold because of parents unwillingness. Also during rice harvesting time in March, April and May, most of the parents were busy with rice harvesting and processing.

Month wise attendance of Formal primary schools parents is presented in the table below-

Table -14: Attendance of CPS /RPS primary schools parents in the monthly parents meeting.

| Name of month | Target | Achievement | Deviation | Remarks |
| --- | --- | --- | --- | --- |
|  | Meeting | Meeting |  |  |
| Janu | 10 | 8 | 2 | Akbarnagar and Nowgaon |
| Feb: | 10 | 8 | 2 | Parikharpar and Nowgaon |
| March | 10 | 6 | 4 | Kalu Miah, Parikharpar, Nowgaon and Gochamara |
| April | 10 | 7 | 3 | Kalu Miah, Parikharpar, Nowgaon |
| May | 10 | 7 | 3 | Imamerchar, Kamarkanda and Pari Ragunathpur |
| June | 10 | 8 | 2 | Parikharpar and Kamarkanda |
| total | 60 | 44 | 16 |  |

3.6  SMC meeting:

In most of the school, SMC meeting held as it was targeted. In January, SMC meeting didn’t hold in Akbarnagar and Nowgaon School. Three additional SMC meeting held at Rajakata and Kamarkanda School. One additional meeting for formation of new SMC committee and another two additional meeting for School renovation discussion.

Table-15: Attendance of SMC members in monthly SMC’s meetings (CPS /RPS).

| Name of month | Target | Achieve | Deviation | Remark |
| --- | --- | --- | --- | --- |
|  | Meeting | Meeting |  |  |
| Jan | 10 | 8 | 2 | Akbarnagar, Nowgaon |
| Feb | 10 | 10 | - |  |
| March | 10 | 12 | - | There were three SMC meeting in Rajakata School for new committee formation and school renovation |
| April | 10 | 10 | - |  |
| May | 10 | 11 |  | One additional meeting in Kamarkandi for Committee formation |
| June | 10 | 10 | - |  |
| Total | 60 | 61 |  |  |

- Project monitoring:

Executive Director and Program Director paid 4 visits to project site during the reporting period.

Project Coordinator and supervisor continuously make their supervision and monitoring visit in the villages and schools for ensuring quality of teaching, improve student’s performance and effective role play of the SMC members. Project Coordinator made 65 visits out of 96. Reason of PC’s less monitoring visit is spent more time to advocacy with UEO and establishment of new ECD center and one formal primary school. Supervisors paid 253 visits out of  240. Supervisors paid more 27 visits than target.

Particulars of monitoring visits are mentioned in the table below.

Table-16: Project monitoring report:

| Designation | Target of visit | Achieve | Deviation | Remarks |
| --- | --- | --- | --- | --- |
| Executive Director | 2 | 2 | - |  |
| Project Director | 2 | 2 | - |  |
| Project Coordinator | 96 | 65 | 31 |  |
| Supervisors | 240 | 253 | 27 |  |

5. Description of Performance in Orphanage:

Activities of Orphanage are conducted to improve health, education and behavior of 55 children.

● Each orphan of orphanage is supplied with clean bed, mosquito net, bed sheet (two for each bed), pillow with cover, three times full meals regularly. In addition to these orphans enjoy use of adequate sanitary latrines, safe water facilities, clean and healthy environment of dwelling dormitory and fresh air. Children have opportunities to play games at field in front of the orphanage daily. These contribute a lot to orphan to keep in good health. Moreover sick children are given primary treatment. All children are in good health and have gained weight.

During the reporting period orphans voluntarily started a vegetable and fruits garden in the premises of orphanage. Project Coordinator and house tutor encourage orphans and appreciated their initiative. Seeds and fertilize are procured by house tutor from local community. The size of the garden is 10 decimals and orphans cultivated local varieties of vegetables and planted papaya trees. They are now consuming daily required vegetables from the garden.

● Orphans are organized into three age group. 4-6 years for ECD group, 6-13 years old orphans are in primary school group and 14-18 years old orphans are in high school group.  It is observed that orphans of primary group are older by age than normal age primary school children. It is because orphan come to orphanage at higher age than normal and could not thing of going to school before recruitment in the orphanage.

Educational performance are observed separately  for TDH-N supported orphans and POPI and local government  supported orphans and information about their result in examination are presented in the tables below:-

Table-17:    Children information of orphanage

| TdH supported |
| --- |
| Class | # of student | drop | Total | Class | # of student | drop | Total |
| ECD |  |  |  |  |  |  |  |
| One | 4 | 0 | 4 | Six | 6 | 0 | 6 |
| Two | - | 0 | - | Seven | 2 | 0 | 2 |
| Three | 6 | 0 | 6 | Eight | 1 | 0 | 1 |
| Four | 4 | 0 | 4 | Nine | 5 | 0 | 5 |
| Five | - | 0 | - | Ten | 2 | 0 | 2 |
| Total | 14 | 0 | 14 | total | 16 | 0 | 16 |

Table-18:    Children information of orphanage

| Local government supported |
| --- |
| Class | # of student | drop | Total | Class | # of student | drop | Total |
| ECD | 11 | 0 | 11 |  |  |  |  |
| One | 1 | 0 | 1 | Six | 1 | 0 | 1 |
| Two | 1 | 0 | 1 | Seven | 1 | 0 | 1 |
| Three | 7 | 0 | 7 | Eight | - | 0 | - |
| Four | 1 | 0 | 1 | Nine | - | 0 | - |
| Five | 1 | 0 | 1 | Ten | - | 0 | - |
| Total | 22 | 0 | 22 | Total | 2 | 0 | 2 |

Table -19: Attendance of Orphanage Student

| Month | Target | Achievement | Deviation | Remarks |
| --- | --- | --- | --- | --- |
| Jan | 99% | 99% | - |  |
| Feb | 99% | 99% | - |  |
| March | 99% | 98% | 1 |  |
| April | 99% | 97% | 2 |  |
| May | 99% | 99% | - |  |
| June | 99% | 99% | - |  |

Tabl-20:    1st terminal exam, result of orphanage (Primary education)

| Name of School | Total Student | Total no. of Student participated in the exam | Deviation | Grade – A (80+) No. of Student | Grade – B (60-79) No. of Student | Grade – C (40-59) No. of Student | Grade – D (-40) No. of Student |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Primary School | 25 | 25 | - | 7 | 10 | 8 | - |
| Secondary School | 19 | 19 | - | 6 | 11 | 2 | - |
| Total | 44 | 44 | - | 13 | 21 | 10 | - |

Thirteen student scored Grad-A, 21 Grade B and 10 Grade C. No student score below 40.

6.  Constraints and problem encountered during reporting period to perform activities:

A number of constraints and problems were encountered during the report period. Some of those were solved, some are at the stage of solution and some remain beyond solution.

●   Teacher turn- over in the middle of the reporting period was another problems encountered

and new teachers were immediately replaced. Total 8 teachers (ECD-6, FPS-2) were resigned

during reporting period. But for lack of plan and fund new 3 teachers did not receive basic

training. The problem was partially solved through monthly refreshers training to them and on

the job training by Project Coordinator and Supervisors.

- Application for govt. registration for Faisal Smriti Pathagar yet to be processed because of land tenure problem. School is situated on the govt. Khash land and Mayor already applied for permanent lease. When we will get lease in than registration will be processed.

- Holding of parents meeting couldn’t possible because of guardians unwillingness to sit for meeting every month. Rather they proposed to hold meeting by monthly or 60 guardian in each month. From April’10 parents meeting conducted according to parents suggestion.

- Sudden resignation of PC from service deferred some scheduled advocacy and networking activities. However, new PC already recruited and he will join soon.

7.  Description of result s achieved and impact of the program:

| Results qualitative | Achievement |
| --- | --- |
| 1. Children have access Early Childhood Development (ECD) program. | Twenty ECD center established and activated within the stipulated time. Total 665 student are enrolled in 20 ECD center while it was targeted 600 children. Because of high demand of ECD support from the parents, additional 65 children were admitted. However, all the 665 children were provided materials and other support within the stipulated budget. There was no drop out during the reporting period. Average attendance rate is 97%. Only in 4 ECD center attendance rate is 95%, a bit lower than target. To increase attendance in those schools, necessary initiative has taken. All the parents (665) were given orientation on child rights during monthly parents meeting. |
| 2. Children have access to primary education organized by POPI. | All the 6 formal Primary Schools activated at the beginning of the year. Total 937 students are enrolled at 6 FPS. During reporting period, total 6 students (0.63% )dropped out. Out of 6, one children died, 1 admitted to Madrasa, 1 went to Mother in law’s house, 1 children started to work as a servant stopping study and another 2 admitted to another school. Children attendance rate is 97% higher than target. All the 24 teachers trained through basic and refresher training. |
| 3. Children have access to community and registered primary schools | Four Community Schools and 6 registered school provided all out planned support. Total 3153 students enrolled in 10 Community and registered schools, higher number than target 2900. Completely achieved the target. During the reporting period, only one children from Gochamara school dropped out. Average attendance rate is 87%, higher than target 85% OVI 1.3.5: At the end of year, hopefully it will be achieved. OVI 1.3.6: By the end of this calendar year, it will be achieved. Out of 50, fortyeight teachers received refreshers. Two teachers couldn’t participate in the training because of other govt. assignment. 1.3.8) No. of participants aware of child rights through quarterly parents teacher meeting Partially achieved. Total 2257 parents were given awareness on child rights. Rest parents will be covered during next semester. All SMC members were given orientation on child rights during monthly meeting. |
| 4. Orphan children have access to education | Total 55 children enrolled until March’10. In April’10 one student left orphanage after passing S.S.C. Total 36 student enrolled (ECD-11, primary school-25) in pre-primary and primary school. Until March, total enrollment in secondary school was 19. One student passed S.S.C. and left orphanage. At present total enrollment in secondary school is 18 instead of 33. No. of student in secondary school kept within 18 because of admission of 11 ECD childrent. 1.4.4) No. of school children promoted to next classes Yet to be achieved. 1.4.5) No. of children completed primary school (grade-5) Yet to be achieved. 1.4.6) No. of children completed secondary school Yet to be achieved. 1.4.7) No. of children received shelter, food and non-food items During the period, all the children were provided shelter, food, education and recreational materials as per plan. |

8.   Lesson learned: During the reporting period following lessons were learned from the

implementation process of the program.

- Mobilization local leaders and public leaders Mayor, MP is must to expedite the process of registration.

- Building good relation with UNO is must to have desired government support.

- More time of top level personnel of implementing agency give encouragement to SMC and some parents to contribute their more support. It also enriches project staff and teachers.

6.  Conclusion:

Community people are very satisfied with management of these schools. SMC and POPI achieve appreciation from Upazila Education Officer, UNO and other elite person of the area. Local Govt. highly appreciated POPI’s support to Orphanage. Because of close monitoring from POPI, orphan did very good result in the 1st terminal exam and also won championship trophy for both football and cricket tournament. In the school enrollment and attendance exceeded targets. ECD concept become very popular and most of the parents have shown interest to admit their kids to ECD center.